## Project Timeline
EASY-A English Project Timline
PROJECT TITLE |  | EASY-A English |  | COMPANY NAME | [5 empty] | MAB Dev Consulting
PROJECT MANAGER |  | Michael Brown |  | DATE | [5 empty] | 2020-03-28
PHASE |  |  | DETAILS | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [11 empty] | Project End
|  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  |  | DEC
| PROJECT WEEK: |  | Enter the date of the first Monday of each month --> | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21
1 | Hiring Application Development Team |  | - Interview Process | bar: MAY 4
- Hiring | bar: MAY 11
2 | Sketching/Wireframing Brainstorm |  | - Brainstorm/Design Wireframe | bar: MAY 18
- Present Wireframes to Client | bar: MAY 25
3 | Design Style Guide |  | - Create Assets, Branding, and Image Resources | bar: JUN 1 to JUN 15
- Complete Design Style Guide to Front-End Developers | bar: JUN 22 to JUN 29
4 | Quality Assurance & Feedback |  | - Develop Front-End of App | bar: JUL 6 to JUL 27
- Develop Back-End Model of App | bar: AUG 3 to AUG 31
- QA Testing | bar: SEP 7 to NOV 16
- App is pushed to production | bar: NOV 23 to DEC 21